Change Request CR-004

Online Spoiled Dairy Product Reporting Module

Introduction

This document presents the formal evaluation and update of Change Request CR-004 from the perspective of Software Configuration Management (SCM) for the Retail Sales System project.

Due to previous poisoning incidents caused by spoiled dairy products, new governmental health regulations now require retailers to report cases in which milk products spoil before their official due date. As a consequence, the client requires the implementation of a new online reporting module capable of collecting and submitting spoiled product information directly from the system.

The purpose of this module is to improve food safety traceability, support regulatory compliance, and reduce public health risks associated with defective dairy products. The module must automatically retrieve and organize information related to spoiled product lots and generate official online reports for health authorities.

The report must include:

- Vendor information

- Lot number

- Delivery date

- Due date

- Spoilage detection details

- Product identification

Additionally, the system must maintain auditability, data integrity, and secure management of sensitive supplier and inventory information.

Since the project follows Agile methodologies and SCM practices, all changes introduced by this request must be documented, version-controlled, validated, and approved before integration into the updated project baseline.

Change Description

Client Request

The client requests the implementation of a new module called:

“Online Spoiled Dairy Product Reporting Module”

The module must:

- Detect and register spoiled dairy product lots

- Generate official spoilage reports

- Submit reports online to regulatory entities

- Collect product information directly from inventory records

- Maintain traceability of affected lots

- Store vendor and delivery information

- Support compliance with food safety regulations

Functional Requirements

Spoiled Dairy Product Reporting Module

CREATE Operations

RF-046

The system shall allow registration of spoiled dairy product incidents.

RF-047

The system shall allow associating spoiled products with a specific vendor.

RF-048

The system shall allow automatic retrieval of lot numbers from inventory records.

RF-049

The system shall allow recording product delivery dates.

RF-050

The system shall allow recording official due dates of dairy products.

RF-051

The system shall allow registration of spoilage detection dates.

RF-052

The system shall allow automatic generation of spoilage reports.

RF-053

The system shall allow online submission of spoilage reports to regulatory authorities.

READ Operations

RF-054

The system shall display spoiled product reports by date, vendor, or lot number.

RF-055

The system shall allow searching spoilage incidents using product identifiers.

RF-056

The system shall display vendor history related to spoiled product incidents.

RF-057

The system shall generate reports of spoiled dairy products by period.

RF-058

The system shall display traceability information for affected product lots.

UPDATE Operations

RF-059

The system shall allow authorized personnel to update spoilage report information.

RF-060

The system shall allow correction of vendor information associated with spoiled lots.

RF-061

The system shall allow updating the status of submitted reports.

DELETE Operations

RF-062

The system shall allow archival of closed spoilage reports.

RF-063

The system shall maintain historical audit logs of archived reports.

Non-Functional Requirements

Security Requirements

RNF-018

The system shall restrict access to spoilage reports based on user roles.

RNF-019

The system shall encrypt sensitive vendor and inventory information.

RNF-020

The system shall maintain audit logs for all spoilage report modifications.

Performance Requirements

RNF-021

The system shall generate spoilage reports within 8 seconds.

RNF-022

The system shall support simultaneous report generation by multiple users.

Availability Requirements

RNF-023

The system shall maintain online availability for report submission processes.

RNF-024

The system shall perform automatic backups of spoilage report records.

Scalability Requirements

RNF-025

The system architecture shall support future integration with additional food safety reporting services.

Maintainability Requirements

RNF-026

The spoilage reporting module shall follow modular architecture principles to facilitate future regulatory updates.

Database Impact

The implementation of the new module requires significant modifications to the database structure in order to support food safety reporting and spoilage traceability.

Proposed New Entities

- SpoiledProductReport

- DairyLot

- VendorTraceability

- SpoilageIncident

- RegulatorySubmission

- DeliveryRecord

- AuditHistory

These modifications require:

- New database relationships

- Migration scripts

- Additional storage for audit records

- Backup policy updates

Impact Level:

High

Current Team Status

The development team currently maintains stable project operations. However, the implementation of a food safety reporting module introduces additional complexity related to compliance regulations and inventory traceability.

| Factor | Status | Justification |
| --- | --- | --- |
| Team maturity | High | The team understands the current architecture |
| Work stability | Moderate | New compliance requirements increase complexity |
| Coordination level | High | Inventory, compliance, and development teams participate |
| Workload impact | High | New reporting and traceability functionalities are required |

Required Skills

| Area | Skill | Reason |
| --- | --- | --- |
| Backend | Reporting API development | Regulatory integration |
| Frontend | Online reporting interfaces | Report visualization |
| Database | Inventory traceability modeling | Lot tracking |
| Security | Data protection | Vendor information security |
| QA | Functional and compliance testing | Regulatory validation |
| SCM | Version control and traceability | Baseline management |
| Compliance | Food safety regulation understanding | Legal compliance |

Effort Estimation

| Activity | Effort | Impact |
| --- | --- | --- |
| Architecture update | High | Reporting integration |
| Development | High | New module implementation |
| Database migration | Medium | New entities |
| Integration | High | Inventory synchronization |
| Testing | High | Compliance validation |
| Documentation | Medium | SCM baseline update |

Total Estimated Effort:

HIGH

The effort level is considered high because the system must support regulatory reporting, inventory traceability, and online submission functionalities.

Team Capacity Impact

The requested change impacts the development team in several ways:

- Increased sprint workload

- Additional compliance validation activities

- Greater integration complexity

- Increased testing scenarios

- Additional coordination with inventory processes

Result:

Moderate-to-High impact on team capacity

Required Time

| Phase | Sprints | Impact |
| --- | --- | --- |
| Planning and analysis | 1 | Requirement analysis |
| Architecture update | 1 | Reporting design |
| Development | 3 | New functionalities |
| Database migration | 1 | Data restructuring |
| Integration | 1 | Inventory synchronization |
| Testing | 2 | Compliance validation |
| Documentation | 1 | SCM update |

Total Estimated Time:

Approximately 9 weeks

Human Resource Estimation

| Role | Quantity | Weeks | Total Cost (USD) |
| --- | --- | --- | --- |
| Backend Developers | 2 | 9 | 14,400 |
| Frontend Developer | 1 | 9 | 8,100 |
| Database Engineer | 1 | 4 | 3,400 |
| QA Tester | 1 | 4 | 2,800 |
| Scrum Master / PM | 1 | 9 | 9,000 |
| Compliance Specialist | 1 | 3 | 3,600 |

Estimated Human Resource Cost:

≈ 41,300 USD

Technological Resources

| Resource | Estimated Cost | Reason |
| --- | --- | --- |
| Online reporting server | 600 USD | Regulatory submissions |
| Database expansion | 400 USD | Traceability records |
| Security certificates | 200 USD | Secure communication |
| Backup infrastructure | 300 USD | Regulatory data protection |
| Monitoring tools | 250 USD | Submission tracking |

Estimated Technology Cost:

≈ 1,750 USD

Total Approximate Cost

| Category | Cost |
| --- | --- |
| Human resources | 41,300 USD |
| Technology | 1,750 USD |

Approximate Total:

≈ 43,050 USD

Contract Impact

| Item | Change | Reason |
| --- | --- | --- |
| Scope | Yes | New compliance module |
| Time | Yes | Additional sprints |
| Budget | Yes | Additional resources |
| Infrastructure | Yes | Online reporting services |
| Agreement | Yes | Regulatory compliance update |

The contract must be formally updated to include the new food safety compliance functionalities.

Mandatory Standards

| Standard | Purpose |
| --- | --- |
| ISO 12207 | Software lifecycle |
| ISO 25010 | Software quality |
| ISO 27001 | Information security |
| Food Safety Regulations | Regulatory compliance |
| Agile SCM | Configuration management |

Risk Analysis

| Risk | Level | Impact |
| --- | --- | --- |
| Incorrect reporting | High | Regulatory penalties |
| Inventory traceability failures | High | Inaccurate reports |
| Integration delays | Medium | Sprint disruption |
| Data inconsistency | Medium | Reporting errors |
| Increased operational costs | Medium | Budget impact |

Agile methodologies and SCM practices help mitigate these risks through iterative validation and continuous monitoring.

SWOT Analysis for Change Request CR-004

Strengths

- Existing inventory management infrastructure

- Experienced development team

- Established SCM practices

Weaknesses

- Increased regulatory complexity

- Additional integration requirements

- Greater dependency on inventory accuracy

Opportunities

- Improved food safety compliance

- Better inventory traceability

- Increased customer trust

Threats

- Regulatory penalties for incorrect reporting

- Increased operational costs

- Delays caused by integration complexity

Guidelines

- Register Change Request CR-004

- Analyze regulatory impact

- Update project backlog

- Design spoilage reporting architecture

- Create traceability entities

- Implement online reporting functionalities

- Perform compliance testing

- Update SCM baseline

- Deploy incrementally

Decision Process

| Factor | Result |
| --- | --- |
| Technical feasibility | Feasible |
| Team capacity | Adjustable |
| Compliance requirements | Achievable |
| Risk | Manageable |
| Business value | High |

Approval Criteria

| Condition | Result |
| --- | --- |
| Technically feasible | Yes |
| Regulatory compliance achievable | Yes |
| Risks manageable | Yes |
| Team adaptable | Yes |
| High business value | Yes |

Final Decision

Result: APPROVED

The Change Request CR-004 is approved due to the necessity of complying with new food safety regulations and improving spoiled product traceability processes.

Although the implementation introduces additional regulatory and technical complexity, the development team can manage the change through Agile methodologies, SCM practices, and controlled incremental development.

The strategic importance of regulatory compliance and customer safety justifies the additional effort, time, and associated costs.

Conclusion

The evaluation confirms that implementing an online spoiled dairy product reporting module is both technically feasible and operationally necessary to comply with new food safety regulations.

The integration of spoilage traceability, automated report generation, and online submission capabilities will significantly improve inventory control, vendor monitoring, and regulatory compliance processes.

From an SCM perspective, the change introduces important modifications to the system architecture, database structure, compliance workflows, and integration mechanisms. However, through proper configuration management and version control practices, the team can implement the change in a controlled and maintainable manner.

The approval of CR-004 strengthens the system’s capability to support future regulatory requirements and enhances the organization’s operational reliability and public safety compliance.