SOFTWARE CONFIGURATION MANAGEMENT

Homework

“Retail Sales System – Configuration Baseline Update”

Author:

Ing. Luis Miguel Fonseca Ponce

Table of Contents

Introduction	3

Current Project Stage	3

Required skills	3

Effort estimation	4

Budget impact	5

Required time	5

Human resources	6

Technological resources	6

Contract impact	7

Mandatory standards	7

Evaluation scales	8

Risk analysis	8

Guidelines	9

Decision process	9

Approval criteria	10

Final decision	10

Conclusion	11

### Introduction

This document presents the formal evaluation of Change Request CR-001, which proposes the development of a web platform for online sales integrated with the current retail sales system. Since this change modifies the original scope of the project, it must be evaluated before approval or rejection. The evaluation includes effort, budget impact, required time, human resources, technological resources, risks, standards, and decision-making process. The project is developed using an Agile methodology; therefore, the change must be analyzed considering incremental development, sprint planning, backlog management, and continuous integration. The evaluation follows Software Configuration Management (SCM) practices adapted to Agile environments to maintain control, traceability, and project stability.

### Current Project Stage

The project is currently in the middle stage of development. In Agile methodology, this means that several sprints have already been completed and the system already contains working modules. Because Agile allows incremental changes, the change can be incorporated, but its impact must still be analyzed.

Table 1: Project status

| Factor | Status | Justification |
| --- | --- | --- |
| Project phase | Middle development | Several sprints completed |
| Change impact | High | New architecture required |
| Risk level | Medium | Late change affects backlog |
| Control required | High | SCM + Agile tracking needed |

The table shows that the project is not in the initial stage, therefore the change must be evaluated carefully because it will affect the sprint backlog and future iterations.

### Required skills

The requested change introduces web development, API integration, and security features.

In Agile projects, new skills may require changes in team capacity and sprint planning.

Table 2: Required skills

| Area | Skill | Reason |
| --- | --- | --- |
| Backend | API / Server | Integration with system |
| Frontend | Web development | Online platform |
| Database | Design / migration | New data |
| Security | HTTPS / Auth | Customer data |
| QA | Testing | New features |
| SCM | Version control | New baseline |
| Agile | Scrum / backlog | Iterative development |

The table shows that the team needs additional knowledge, which justifies the increase in effort and resources.

### Effort estimation

In order to make a correct decision about the approval of Change Request CR-001, it is necessary to estimate the development effort and the approximate cost required to implement the new functionality.

Since the project is developed using an Agile methodology, the effort is estimated considering iterations (sprints), team capacity, and additional tasks required for web integration, testing, and configuration management.

The cost estimation is based on the number of working hours, the number of team members, and the additional technological resources required.

For formal SCM evaluation, the following scale is used.

Table 3: Effort scale

| Level | Hours | Meaning |
| --- | --- | --- |
| Low | 1–40 | Small change |
| Medium | 41–120 | Moderate |
| High | 121–300 | Large |
| Very High | 300+ | Critical |

Table 4: Effort per task

| Activity | Estimated Effort | Reason |
| --- | --- | --- |
| Architecture update | Medium | New web structure required |
| Web platform development | High | New module |
| API integration | Medium | Connect existing system |
| Database update | Medium | New tables |
| Security implementation | Medium | HTTPS / authentication |
| Testing and QA | High | New scenarios |
| Documentation update | Low | Baseline update |
| Sprint planning and backlog update | Medium | Agile process |

Total effort level = High

The effort is considered high because the change introduces a new system component and requires several development iterations.

### Budget impact

Agile projects allow flexible scope, but budget must still be evaluated.

Table 5: Budget impact

| Factor | Impact | Reason |
| --- | --- | --- |
| More hours | Yes | More work |
| More team | Yes | New skills |
| Servers | Yes | Web system |
| Security tools | Yes | HTTPS |
| Reuse code | Reduces cost | Existing modules |

Result: Moderate impact

The budget increases, but the business value also increases, which justifies approval.

### Required time

In Agile, time is measured in sprints.

Table 6: Estimated time in sprints

| Phase | Sprints | Duration |
| --- | --- | --- |
| Design update | 1 sprint | 1 week |
| Development | 3 sprints | 3 weeks |
| Integration | 1 sprint | 1 week |
| Testing | 2 sprints | 2 weeks |
| Documentation | 1 sprint | 1 week |

Total ≈ 8 weeks

The change can be implemented incrementally without stopping the current development.

Assuming the following average cost per developer per week.

Table 7: Team cost estimation

| Role | Qty | Cost per week (USD) | Weeks | Total |
| --- | --- | --- | --- | --- |
| Developer | 2 | 800 | 8 | 12800 |
| Web developer | 1 | 900 | 8 | 7200 |
| Database engineer | 1 | 850 | 4 | 3400 |
| Tester | 1 | 700 | 4 | 2800 |
| Scrum master / PM | 1 | 1000 | 8 | 8000 |

Estimated human resource cost = 34,200 USD

Table 8: Technological cost estimation

| Resource | Estimated cost | Reason |
| --- | --- | --- |
| Web server | 500 USD | Hosting |
| SSL certificate | 150 USD | Security |
| Database upgrade | 400 USD | Storage |
| CI/CD tools | 300 USD | Agile integration |
| Testing tools | 250 USD | QA |

Estimated technology cost = 1,600 USD

Table 9: Total approximate cost

| Category | Cost |
| --- | --- |
| Human resources | 34,200 USD |
| Technology | 1,600 USD |
| Total | 35,800 USD |

Approximate cost: ≈ 36,000 USD

### Human resources

Agile teams are usually small, but new functionality may require more roles.

Table 7: Human resources

| Role | Qty | Reason |
| --- | --- | --- |
| Developer | 2 | Coding |
| Web dev | 1 | UI |
| DB engineer | 1 | Data |
| Tester | 1 | QA |
| Scrum master / PM | 1 | Coordination |

The table shows that the team must be extended to maintain sprint velocity.

The estimated cost is considered moderate for a system extension that adds online sales capability.

The effort is high because the change affects architecture, database, security, and testing, but the Agile methodology allows the work to be divided into sprints, reducing risk and making the change manageable.

Because the cost is acceptable and the business value is high, the change request can be approved.

### Technological resources

Table 8: Technology

| Resource | Needed | Reason |
| --- | --- | --- |
| Web server | Yes | Online |
| App server | Yes | API |
| DB server | Yes | Data |
| SSL | Yes | Security |
| Git | Yes | Version |
| CI/CD | Yes | Agile integration |

Agile requires continuous integration, therefore CI/CD tools are included.

### Contract impact

Even in Agile, scope change may affect contract.

Table 9: Contract impact

| Item | Change | Reason |
| --- | --- | --- |
| Scope | Yes | New feature |
| Budget | Yes | More work |
| Time | Yes | More sprints |
| Agreement | Yes | Formal update |

Contract must be updated to include the new backlog items.

### Mandatory standards

Table 10: Standards

| Standard | Use |
| --- | --- |
| ISO 12207 | Lifecycle |
| ISO 25010 | Quality |
| ISO 27001 | Security |
| Data protection | Customers |
| Agile SCM | Version control |

Online systems must follow security rules.

### Evaluation scales

Table 11: Scale

| Factor | Scale |
| --- | --- |
| Effort | Low / Medium / High |
| Cost | Low / Medium / High |
| Risk | Low / Medium / High |
| Time | Short / Medium / Long |
| Impact | Low / Medium / High |

Result:

| Factor | Level |
| --- | --- |
| Effort | High |
| Cost | Medium |
| Risk | Medium |
| Time | Medium |
| Impact | High |

Tables allow objective decision making.

### Risk analysis

Table 12: Risks

| Risk | Level | Mitigation |
| --- | --- | --- |
| Security | Medium | HTTPS |
| Inventory sync | Medium | Central DB |
| Delay | Medium | Sprint plan |
| Complexity | High | Modular |
| Cost | Medium | Budget control |

Agile helps reduce risk through incremental delivery.

### Guidelines

Table 13: SCM + Agile process

| Step | Action |
| --- | --- |
| 1 | Register CR |
| 2 | Impact analysis |
| 3 | Feasibility |
| 4 | Estimate |
| 5 | Contract review |
| 6 | Risk |
| 7 | Change Control Board |
| 8 | Update backlog |
| 9 | New baseline |

Agile adds backlog update.

### Decision process

Table 14: Final evaluation

| Factor | Result |
| --- | --- |
| Technical | Feasible |
| Economic | Acceptable |
| Time | Acceptable |
| Risk | Medium |
| Contract | Adjustable |
| Business value | High |

### Approval criteria

Table 15: Rules

| Condition | OK |
| --- | --- |
| Feasible | Yes |
| Cost acceptable | Yes |
| Time acceptable | Yes |
| Risk manageable | Yes |
| High value | Yes |
| Contract update possible | Yes |

Result: APPROVED

### Final decision

The Change Request CR-001 was approved after performing the technical, economic, operational, and risk analysis following the formal Software Configuration Management (SCM) process within an Agile development environment.

The approval decision was made because the benefits of the change are greater than the impact generated on the project, and because the team can incorporate the new functionality into the planned iterations without compromising the stability of the system.

To justify the decision, the main evaluation factors are presented below.

Table 16: Decision

| Evaluated factor | Result | Justification |
| --- | --- | --- |
| Technical feasibility | Approved | Current architecture supports web integration |
| Cost impact | Acceptable | Moderate increase |
| Time impact | Acceptable | Can be divided into sprints |
| Risk level | Medium | Manageable with best practices |
| Available resources | Sufficient | Team can be extended |
| Contract impact | Adjustable | Can be formally updated |
| Business value | High | Enables online sales |
| Agile compatibility | High | Can be added to backlog |

The table shows that all evaluation criteria meet the conditions required for approval.

### Conclusion

The change was considered technically feasible because the current system architecture allows extension through web services without the need to redesign the existing modules.

From the economic perspective, the additional cost is moderate, since current components such as the product module and the inventory module can be reused, reducing the financial impact.

Regarding time, the change can be implemented using Agile iterations, distributing the work across several sprints, which prevents disruption of the normal development flow.

The risk level is considered medium because integrating a web platform increases system complexity, but this risk can be controlled through incremental testing, continuous integration, and configuration control.

It was also determined that the contract can be updated without conflict, allowing the new system scope to be formally included.

The most important factor for approval was the high business value, since adding online sales significantly increases business opportunities and improves the usefulness of the system.

Additionally, Agile methodology facilitates the incorporation of the change because it allows backlog updates, sprint replanning, and incremental delivery without stopping the project.